## Slide 1: Project Management Plan Courtney Tatum, Designer July 30, 2012
Bryant & Stratton College’s ASVAB Prep Course:

## Slide 2: During this presentation, we will…
Discuss the current status of the course development
Identify needs and challenges that will be faced during implementation
Determine what will be needed to meet challenges
Agree on a timeline for the completion of course implementation

## Slide 3: ASVAB Prep: as it currently stands
Course Objectives-
Upon completion of the course, students will be able to:
Utilize test taking skills and best practices while taking practice and official ASVAB tests;
Overcome weaknesses and challenges through discussions and interactions with classmates and instructors;
Facilitate their own learning in study groups with student-teaching opportunities;
Achieve at least a 40 on the official ASVAB, qualifying the student for entry into any branch of the military;
Improve baseline test scores by at least 20%.

## Slide 4: ASVAB Prep: as it currently stands
Following the ADDIE Model of instructional design, the following are tasks have been or need to be completed:
Analyze- context and needs analysis has been completed to determine what needs are to be met
Design- The learning design has been completed to determine how those needs will be met
Development- Prototype development is in progress using the LMS, WebTycho
Implementation- development of the finished course in the official LMS must be completed
Evaluation- testing and evaluation of the course will be conducted to ensure course objectives are met

## Slide 5: What is needed to complete the Implementation phase?
Access to Bryant & Stratton’s LMS of choice, ANGEL
Selection of specific course content- subject matter experts will need to review materials available and determine which will be used and in what capacity
Faculty assigned to facilitate the course- liberal arts and general education faculty will be needed as they can facilitate the course throughout the numerous subjects
Buy-in from the local military recruiters to use the course- recruiters will be needed for their input in the course, as well as to mentor students and promote the class
Evaluation tools- using strategies discussed by Gooler (1980) in his article, “Formative evaluation strategies for major instructional development projects.”

## Slide 6
Schedule of Tasks
Task | Resources Needed | Dates of completion
Completion of prototype course in Webtycho | Instructional Designer, Peer reviewers, mentors | 8/19/2012
Final selection of course content | Subject matter experts, instructors, text books, military recruiters | Today- 9/17/2012
Development of learning activities | Subject matter experts, instructors, text books | Today- 9/17/2012
Final implementation in ANGEL and testing | ID, BSC IT technicians, instructors, online learning department support | 9/1- 10/1/2012
Course Begins | EVERYONE | 1/1/2013
Evaluation of Course Effectiveness |  | Ongoing
Marketing and Advertisement | Military Recruiters, BSC marketing and communications personnel | Ongoing

## Slide 7: Problems we may face…
Challenge | Solution
ASVAB includes 10 subjects which includes math, writing, reading, science, and technical problems The fast-paced, 8 week course will need to cover all subject areas Students must not be overwhelmed with the amount of content to be covered | General studies and liberal arts faculty with a broad discipline will be used to instruct the course The instructional designer will ensure that the course is organized and easy to follow Instructors and ID will collaborate with military recruiters using reference books to determine what is needed to know versus what is good to know

## Slide 8: Problems we may face…
Challenge | Solution
Subject matter content and delivery must be interactive Activities and delivery of information must take many forms to cater to all types of learners In addition to the learning that must occur, a sense of community and togetherness must also be fostered to support students | ID must integrate the use of quizzes and activities using Drupal, Powerpoints, and multimedia. IT specialists will be needed for this task Collaboration must occur with instructors to being a physical classroom aspect to the online classroom Discussion boards must be effectively to enhance learning activities. Articles and supplemental reading must be acquired

## Slide 9: Summary
We are set to launch the first class in January of 2013
Subject matter experts will be integral in determining the final content of the course
IT specialists and ID will need to develop learning activities and evaluations based on the content chosen
We will need to schedule collaborative meetings throughout this process to ensure all parties are on the same page

## Slide 10: References
Gooler, D. D. (1980, Spring). Formative evaluation strategies for major instructional development projects. Journal of Instructional Development, 3(3), 7-11.
Morrison, Morrison, G.R., S. Ross, and J. E. Kemp. (2007). Designing effective instruction (5th ed.). New York: John Wiley and Sons. ISBN: 0-470- 07426-4.

## Slide 11: Any Questions?
Presented by Courtney Tatum, Instructional Designer